## POAM
Meridian Pay Solutions — Plan of Action & Milestones (POA&M)
Remediation roadmap tied to Risk Register findings ¦ Fictional Case Study for Portfolio Purposes ¦ Last Updated: 2026-Q1
POAM ID | Related Risk ID(s) | NIST CSF Function | Weakness / Finding | Remediation Action | Resources Required | Risk Rating | Milestone Owner | Start Date | Target Completion Date | % Complete | Status | Notes
POAM-01 | RISK-01 | Govern | No formal enterprise risk management (ERM) program; cybersecurity risk tracked ad hoc | Establish a cross-functional risk committee (Security, Engineering, Legal/Compliance, Finance); adopt a formal risk register and quarterly review cadence; define risk appetite and tolerance statements | Security/GRC Analyst time; executive sponsorship; risk management tooling (e.g., GRC platform or structured spreadsheet) | High | Head of Security | 2026-02-01 | 2026-05-01 | 10% | In Progress | Risk register from this assessment serves as the initial baseline
POAM-02 | RISK-02 | Govern | No dedicated CISO/security executive; security has no direct board/executive risk reporting line | Define and fill a CISO or VP of Security role (or formally expand current security leader's scope/title with direct executive reporting line); establish quarterly security posture reporting to executive leadership | Budget approval for new/expanded role; executive sponsorship | High | CEO / CTO | 2026-02-01 | 2026-07-01 | 0% | Not Started | Pending budget approval in next planning cycle
POAM-03 | RISK-03 | Govern | No formal vendor security risk assessment process for third parties with access to sensitive data | Develop a vendor risk tiering model; implement a standardized security questionnaire (e.g., based on SIG Lite) and require SOC 2 reports for Tier 1/2 vendors; establish annual vendor reassessment cadence | GRC Analyst time; vendor questionnaire template/tooling; Legal/Procurement coordination | High | Head of Security / Procurement | 2026-03-01 | 2026-06-01 | 0% | Not Started | Coordinate with Legal on integrating into contract renewal process
POAM-04 | RISK-04 | Identify | Asset inventory partially manual and not continuously updated | Implement automated asset discovery/CMDB tooling integrated with AWS and SaaS environments; deprecate manual spreadsheet as source of truth | Asset management/CMDB tooling budget; IT/Engineering implementation time | Medium | IT Manager | 2026-02-15 | 2026-05-15 | 20% | In Progress | Evaluating two CMDB/asset discovery tools
POAM-05 | RISK-05 | Identify | No formal, recurring vulnerability management program | Implement scheduled vulnerability scanning (e.g., weekly for production, monthly for non-production); define patch SLAs by severity; assign clear remediation ownership | Vulnerability scanning tooling; Security Engineering time | High | Security Engineering | 2026-02-01 | 2026-04-15 | 30% | In Progress | Scanning tool selected; rollout to staging complete, production pending
POAM-06 | RISK-06 | Protect | MFA not universally enforced across all internal systems | Conduct inventory of internal systems lacking MFA; enforce MFA via Okta for all internal applications supporting SSO; implement compensating controls (e.g., VPN + MFA) for legacy systems that cannot integrate with SSO | IT/Security Engineering time; potential licensing costs for MFA on legacy systems | High | IT Manager / Security Engineering | 2026-02-01 | 2026-04-01 | 40% | In Progress | 80% of internal apps now behind Okta SSO+MFA; legacy ticketing system remaining
POAM-07 | RISK-07 | Protect | No formally scheduled periodic access reviews | Implement quarterly access recertification process for all systems handling Confidential/Restricted data; assign business owners to review and attest to access lists | GRC Analyst time; access review tooling or structured tracking process | Low | IT Manager | 2026-03-01 | 2026-05-01 | 0% | Not Started | Process design phase; first review cycle targeted for Q2 2026
POAM-08 | RISK-08 | Protect | Security awareness training is generic, not role-based | Develop role-based training tracks (engineering, support/operations, finance, executive) with phishing simulation program for high-risk roles | Security awareness training platform; HR coordination | Low | Head of Security / HR | 2026-04-01 | 2026-08-01 | 0% | Not Started | Evaluating training platform vendors
POAM-09 | RISK-09, RISK-10 | Detect | No centralized SIEM/log correlation; no formal SOC process or detection use cases | Deploy centralized SIEM (or cloud-native equivalent, e.g., AWS Security Hub + GuardDuty) to correlate logs across cloud, application, and identity systems; define initial set of high-priority detection use cases; establish alert triage process with defined coverage hours | SIEM/security monitoring tooling budget; Security Engineering + SOC Analyst implementation time; potential MSSP evaluation for 24/7 coverage | Critical | Security Engineering / SOC | 2026-02-01 | 2026-06-01 | 15% | In Progress | Top remediation priority; GuardDuty enabled in production, full SIEM rollout in progress
POAM-10 | RISK-11 | Respond | No formal, documented incident response plan | Develop and document a formal incident response plan including severity classification, escalation paths, roles/responsibilities (RACI), and communication templates; conduct tabletop exercise to validate | Security/GRC Analyst time; cross-functional participation (Engineering, Legal, Comms) for tabletop exercise | Critical | Head of Security | 2026-02-01 | 2026-04-30 | 25% | In Progress | Draft plan in review; tabletop exercise scheduled for April 2026
POAM-11 | RISK-12 | Respond | No defined breach notification procedure mapped to regulatory timelines | Document breach notification workflow mapped to applicable state breach notification laws, card network rules, and contractual obligations; define legal/compliance escalation triggers and notification templates | Legal/Compliance time; coordination with outside counsel as needed | Medium | Legal/Compliance / Head of Security | 2026-03-01 | 2026-05-15 | 0% | Not Started | To be incorporated as an annex to the incident response plan (POAM-10)
POAM-12 | RISK-13 | Recover | Disaster recovery plan untested via tabletop or live failover in 18+ months | Conduct DR tabletop exercise to validate current plan; follow with a live failover test for critical production systems; update RTO/RPO documentation based on results | Engineering/IT time; potential downtime window coordination for live failover test | Medium | IT Manager / Engineering | 2026-03-15 | 2026-06-15 | 0% | Not Started | Tabletop exercise to be scheduled first; live failover test to follow

## Summary Dashboard
POA&M Summary Dashboard
Status and risk distribution across all open remediation items
By Status
Not Started | 6
In Progress | 6
Completed | 0
Delayed | 0
By Risk Rating
Critical | 2
High | 5
Medium | 3
Low | 2
Average % Complete (All Items) | 11.67%